## Sheet1
PROJECT START | 2021-04-01
|  |  | 2021-04-01 | [6 empty] | 2021-04-08 | [6 empty] | 2021-04-15 | [6 empty] | 2021-04-22 | [6 empty] | 2021-04-29 | [6 empty] | 2021-05-06 | [6 empty] | 2021-05-13 | [6 empty] | 2021-05-20 | [6 empty] | 2021-05-27
 | time axis 2021-04-01 to 2021-06-02
TASK | START | END | time axis 2021-04-01 to 2021-06-02
T1 | 2021-04-01 | 2021-04-05
T2 | 2021-04-06 | 2021-04-13
T3 | 2021-04-06 | 2021-04-14
T4 | 2021-04-06 | 2021-04-09
T5 | 2021-04-06 | 2021-04-11
T6 | 2021-04-06 | 2021-04-12
T7 | 2021-04-12 | 2021-04-17
T8 | 2021-04-18 | 2021-05-16
T9 | 2021-05-03 | 2021-05-26
T10 | 2021-05-17 | 2021-05-26
T11 | 2021-05-13 | 2021-05-26
T12 | 2021-05-27 | 2021-06-01 | 2021-06-02: Finish

## Sheet2
PROJECT | Ứng dụng điểm danh trong lớp học
[5 empty] | Software | Page | User
[5 empty] | MobiApp | Login | teacher, student
TASK | CONTENT | EFFORT (persion-days) | DURATION (days) | DEPENDENCIES |  | Profile
T1 | Xác định yêu cầu | 2 | 4 |  |  | Reset Password
T2 | Thiết kế giao diện detector software | 7 | 7 | T1 |  | Schedule
T3 | Thiết kế giao diện mobiapp | 7 | 8 | T1 |  | Statistics
T4 | Thiết kế giao diện management software | 3 | 3 | T1 | Management Software | Login | collaborator, administrators
T5 | Thiết kế csdl | 5 | 5 | T1 |  | Profile
T6 | Thiết kế thuật toán nhận diện | 6 | 6 | T1 |  | Reset Password
T7 | Kết nối dữ liệu | 9 | 5 | T5 |  | Class List | collaborator
T8 | Thiết kế các chức năng ứng với từng page | 60 | 28 | T2,T3,T4,T7,T6 |  | Account List | administrators
T9 | Gộp code và test | 23 | 23 | T8 |  | Statistics | collaborator
T10 | Chỉnh sửa và thêm chức năng | 18 | 9 | T8 | Detector Software | Attendance
T11 | Cải tiến thuật toán nhận diện | 20 | 13 | T6
T12 | Hoàn thiện và viết document | 3 | 5 | T9